## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding full project flow and requirements | Discussed with mentor and reviewed project documentation
Sprint 1 | Day 4 | Confusion while revising Python concepts in project context | Practiced logic-building problems and revised concepts
Sprint 2 | Day 8 | Errors while integrating Google Sheets API | Rechecked credentials and tested API connection
Sprint 2 | Day 11 | Confusion in understanding NLP concepts | Watched tutorials and tested small NLP examples
Sprint 3 | Day 16 | Social media API authentication failures | Regenerated API keys and corrected endpoint
Sprint 3 | Day 19 | Errors in automatic content generation | Improved prompts and tried fallback mechanism
Sprint 3 | Day 21 | Handling multiple content variations was confusing | Implemented loop-based logic
Sprint 4 | Day 24 | Confusion in sentiment analysis results | Took the help of mentor
Sprint 4 | Day 26 | Issues with Slack webhook not sending messages | Rechecked webhook URL and tested with sample data
Sprint 4 | Day 28 | Streamlit errors | Fixed import issues and tested locally

## Sprint Backlog
du
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundations and Prerequistes for doing the project | 23rd sep | 7th Oct | Deekshith K | Learnt fundamentals of python | Done |  | Introduction | Installed Python and Jupyter succesfully | Understood Naming conventions in python | Learnt datatypes in python | Deepend knowledge in python fundementals | Practiced python programming | Learnt flow controll statements an loops | learnt strings in python | Revised previously studied concepts | Practiced python programm studied till now | Learnt string methods and python function | Practiced functions | Practiced functions deeply | Learnt Functions clearly
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | Deekshith K | Understood Project workflow, structure, NLP, Google Sheets Integration | Done |  | Learnt OOPs | Understood Packages, Modules, Importing | Understood NLP and Programmed using NLTK library | Deep dived into NLTK, Spacy Libraries | Practiced programming using NLTK and Spacy libraries | Understood about the project and its uses | Explained about project & some terms related to project | Learnt how to Create, Activate and Deactivate Virtual env | Learnt about transformers | Got an oppurtunity to explain about project infornt of my team | Practiced Hugging Face transformers | Revised all the previous contents | Revised Transformers - NLP | Google sheet API Integration completed
3 |  | Social Media Integration, Content Creation, Optimization | 23rd Oct | 6th Nov | Deekshith K | Hands-on experience with social media APIs and implemented content generation. | Done |  | Understood Twitter API integration | Twitter API integrated succesfully and tested | Tried Facebook API Integration | Completed Facebook API Integration | Interactive session | Practiced API integration | Understood about generating mock data | Generated content using llm and Groq API | Learnt how to write into google sheet using program | Understood LLM fundamentals | Practiced generating content and connecting with google sheet | Interactive session | Understood how to generate different variations of content | Practiced generating different content variations
4 |  | Learnt Sentiment Analysis, Slack Integration, A/B Testing, Deployment on Streamlit | 6th Nov | 20th Nov | Deekshith K | Learnt Sentiment Analysis, Slack Integration, A/B Testing, Deployment on Streamlit | Done |  | Understood how APIs work | Understood APIs in detail | Revised and worked on APIs | Completed Assignment | Interactive Session | learnt how to optimize contents | Understood and worked on sentiment analysis | Implemented Slack integration in the program | Understood A/B Testing | Used some resources to learn more about A/B testing. | Revised Content generation, optimization, sentiment analysis, and A/B testing | Understood the project workflow | Preparation for mock presentation | Mock Presenatation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 3- Completed
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 25th Sept | 7th oct | Deekshith K | Writing clean, structured, and reusable python code | Stop skipping practice thinking I already knew everything | Continue regular Coding Practice and daily learning sessions | Revised Complete python fundementals and strengthened logic through mini coding tasks
2 | Sprint 2 | 8th Oct | 22nd Oct | Deekshith K | Working with APIs and integrations building structured project architecture | Stop delaying API testing after setup | Improving understanding of NLP concepts | Integrated Google hseets API and Organised project folder and workflow
3 | Sprint 3 | 23rd Oct | 6th Nov | Deekshith K | Working with social media API's and content generation | Skipping proper error handling and assuming the code would work | Improving Content generation features | Implemented Twitter and FaceBook API succesfully and , created different variations of generated contents, and posted them automatically
4 | sprint 4 | 6th Nov | 24th Nov | Deekshith K | Start Sentiment Analysis, A/B testing and Slack Notifications | Ignoring minor bugs during testing | Improving UI and user experience in Streamlit | Built sentiment analysis, A/B testing module, Integrated Slack notifications and Deployed application using Streamlit